## Slide 1
STAR GLOBAL COLLEGE
WEEK 1 / PROJECT CHARTER
1. Project title
Name the process and the improvement you want to achieve.
Exemplar
Your Project
[Enter your project title]
Process: [Enter process]
Project leader: [Enter name]
Organization: [Enter organization]
Replace the bracketed prompts on the right with your project details.
Example Services is a fictional training example. All student response areas are editable.
Reducing Customer Support Response Time
Process: Customer support email queue
Project leader: Alex Morgan
Organization: Example Services

## Slide 2
STAR GLOBAL COLLEGE
WEEK 1 / PROJECT CHARTER
2. Problem statement
Describe what is happening, where, when, and how large the problem is.
Exemplar
Your Project
During [period], [number or percentage] of [items] in [process/location] experienced [problem].
Current performance: [Enter baseline]
Expected performance: [Enter requirement]
Use observed facts. Keep suspected causes and proposed solutions for later project work.
Example Services is a fictional training example. All student response areas are editable.
During September, 180 of 600 customer support emails (30%) received their first response after 24 hours. The service target is no more than 10%. The cause has not yet been confirmed.

## Slide 3
STAR GLOBAL COLLEGE
WEEK 1 / PROJECT CHARTER
3. Business case
Explain why solving this problem matters to the organization.
Exemplar
Your Project
This problem affects [customers, employees, or business area].
The impact is [cost, time, quality, or service impact].
Improving this process supports [business priority].
Add a cost estimate only when you can explain the calculation.
Example Services is a fictional training example. All student response areas are editable.
Late responses affect approximately 180 customer emails per month. They can lead to repeat contacts and additional follow-up work. This project supports the organization’s customer service goals.

## Slide 4
STAR GLOBAL COLLEGE
WEEK 1 / PROJECT CHARTER
4. Goal statement
Include the metric, baseline, target, and completion date.
Exemplar
Your Project
Reduce/increase [metric] from [baseline] to [target] by [completion date].
Baseline: [Enter value and unit]
Target: [Enter value and unit]
Due date: [Enter date]
The target is a planned outcome. The project has not achieved it yet.
Example Services is a fictional training example. All student response areas are editable.
Reduce the percentage of customer support emails receiving their first response after 24 hours from 30% to 10% or less by the end of Week 5.
Chart: 
| Baseline | Planned target
Emails after 24 hours | 0.3 | 0.1

## Slide 5
STAR GLOBAL COLLEGE
WEEK 1 / PROJECT CHARTER
5. Project scope
Set clear boundaries so the project stays manageable.
Exemplar
Your Project
IN SCOPE
[Enter process, location, and start/end points]
OUT OF SCOPE
[Enter what this project will exclude]
Start: Email received
End: First response sent
Example Services is a fictional training example. All student response areas are editable.
IN SCOPE
Customer support emails for the U.S. team, from receipt to first response.
OUT OF SCOPE
Phone support, social media messages, and final case resolution.

## Slide 6
STAR GLOBAL COLLEGE
WEEK 1 / PROJECT CHARTER
6. Project team
Identify who leads, supports, and approves the project.
Exemplar
Your Project
Sponsor: [Enter name/title]
Project leader: [Enter name]
Process owner: [Enter name/title]
Team members: [Enter names/roles]
Confirm availability and responsibilities with each person.
Example Services is a fictional training example. All student response areas are editable.
Sponsor: Customer Service Director
Project leader: Alex Morgan
Process owner: Support Supervisor
Team members: Two support representatives and one data analyst

## Slide 7
STAR GLOBAL COLLEGE
WEEK 1 / PROJECT CHARTER
7. Project timeline
Set a target completion date for each DMAIC phase.
Exemplar
Your Project
Define completed by: [Date]
Measure completed by: [Date]
Analyze completed by: [Date]
Improve completed by: [Date]
Control completed by: [Date]
Submit your completed charter after filling in all seven sections.
Example Services is a fictional training example. All student response areas are editable.
Week 1: Define, project charter
Week 2: Measure, baseline data
Week 3: Analyze, root cause evidence
Week 4: Improve, pilot test
Week 5: Control, monitoring and handoff
Define
W1
Measure
W2
Analyze
W3
Improve
W4
Control
W5