## Slide 1
STAR GLOBAL COLLEGE
WEEK 5 / SUSTAIN & COMPLETE
1. Your final results
Summarize what changed and compare the result with your original goal.
Exemplar
Your Project
Main metric: [Enter]
Baseline: [Count, total, rate]
Latest result: [Count, total, rate]
Goal: [Enter]
Conclusion and limitations: [Enter]
Use the same metric definition. Distinguish pilot findings from longer-term results.
Example Services is a fictional training example. Replace prompts with your own project evidence.
Metric: Late first responses
Baseline: 180 of 600 = 30%
Pilot: 15 of 150 = 10%
Goal: 10% or less
The pilot met the target. Longer follow-up is still needed.

## Slide 2
STAR GLOBAL COLLEGE
WEEK 5 / SUSTAIN & COMPLETE
2. Standard work
Document the steps people should follow to keep the new process working.
Exemplar
Your Project
1. [Enter step]
2. [Enter step]
3. [Enter step]
4. [Enter step]
5. [Enter step]
Document owner: [Enter]
Add the approved procedure or updated process map. Confirm affected staff understand the changes.
Example Services is a fictional training example. Replace prompts with your own project evidence.
1. Route incoming emails to available staff.
2. Check unassigned emails each morning.
3. Review queue balance during the day.
4. Escalate emails nearing 24 hours.
5. Record exceptions for review.

## Slide 3
STAR GLOBAL COLLEGE
WEEK 5 / SUSTAIN & COMPLETE
3. Control plan
Specify what will be monitored, how often, and by whom.
Exemplar
Your Project
Metric: [Enter]
Method or data source: [Enter]
Frequency: [Enter]
Owner: [Enter]
Target: [Enter]
Record location: [Enter]
Use a monitoring method appropriate to your process and available data.
Example Services is a fictional training example. Replace prompts with your own project evidence.
Metric: Percentage of late first responses
Method: Support system report
Frequency: Weekly
Owner: Support Supervisor
Target: 10% or less
Record: Weekly monitoring log

## Slide 4
STAR GLOBAL COLLEGE
WEEK 5 / SUSTAIN & COMPLETE
4. Response plan
Explain what happens if performance falls below the expected level.
Exemplar
Your Project
Trigger: [Enter condition]
Action and owner: [Enter]
Response time: [Enter]
Follow-up check: [Enter]
A target-based response trigger is a management rule. It is not a statistical control limit.
Example Services is a fictional training example. Replace prompts with your own project evidence.
Trigger: Weekly late-response rate exceeds 10%.
Action: Supervisor reviews unassigned work, staffing, and routing errors within one business day.
Follow-up: Record corrective action and check the next reporting period.

## Slide 5
STAR GLOBAL COLLEGE
WEEK 5 / SUSTAIN & COMPLETE
5. Monitoring graph
Add a run chart to show whether the improvement continues over time.
Exemplar
Your Project
[Insert your monitoring graph here]
Metric and period: [Enter]
Change date: [Enter]
What does the graph show? [Explain]
Use a suitable control chart when you have enough data and can justify the chart and calculated limits.
Example Services is a fictional training example. Replace prompts with your own project evidence.
Plot the metric in time order. Mark when the change began and include the target.
Chart: 
| B1 | B2 | B3 | B4 | P1 | F1 | F2 | F3
Late responses | 0.28 | 0.32 | 0.3 | 0.3 | 0.1 | 0.08 | 0.1 | 0.09
Target | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
B: Baseline P: Pilot F: Follow-up Gold: 10% target

## Slide 6
STAR GLOBAL COLLEGE
WEEK 5 / SUSTAIN & COMPLETE
6. Process handoff
Confirm who takes responsibility after the project ends.
Exemplar
Your Project
Process owner: [Enter]
Documents provided: [Enter]
Training completed: [Enter]
Review schedule: [Enter]
Acceptance and date: [Enter]
Record actual approvals. Keep pending actions visible until the responsible person accepts them.
Example Services is a fictional training example. Replace prompts with your own project evidence.
Process owner: Support Supervisor
Documents: Routing procedure and control plan
Training: Support team briefing
Review schedule: Weekly for the next month
Acceptance: Process owner approval pending

## Slide 7
STAR GLOBAL COLLEGE
WEEK 5 / SUSTAIN & COMPLETE
7. Final project submission
Bring your five weekly assignments together into one project presentation.
Exemplar
Your Project
Project title: [Enter]
Student name: [Enter]
[Confirm all five weeks are complete]
[Attach supporting data/calculations]
[Remove confidential information]
Final file name: [Enter]
Submit through the designated course project submission link. Certification depends on meeting the program requirements.
Example Services is a fictional training example. Replace prompts with your own project evidence.
Week 1: Project charter
Week 2: Process map and baseline
Week 3: Root cause evidence
Week 4: Improvement and pilot results
Week 5: Standard work and control plan
Include your data and calculations.